---draft---	IAIA’05 suggested timelines/deadlines (in-house)

Bolded items are published. *Indicates a date that has already been published.

Updated 2/22/05

# 31 December	Early Bird registration ends*

31 January		Student fee waiver applications due

# 28 February	Abstracts due. Note:  online abstract submission page discontinued 1 March; no new abstracts accepted.

# 1 March	• Regular registration rate ends*

14 March	• All abstracts reviewed by session chairs (abstracts should have been reviewed on a weekly basis, so although many will come in on deadline, this 11 days should allow enough time.)

• Session chairs should have contacted all presenting authors regarding acceptance status and advising of registration deadline (this assumes Wes & Charlotte trust session chairs’ judgment and/or have also been reviewing session chairs’ acceptance status)

22 March	• Deadline for presenting author’s registration.  Note: the published date was 1 March*

• Last day authors can make changes to abstracts. Online update page discontinued 28 February.

28 March	Registrations processed

30 March	Presentations without presenting author registered dropped from program (status indicated online); session chairs prepare or adjust detailed schedule (allows chairs 16 days)

# 31 March	• Exhibitors deadline

• Tech visit deadline

• Delegate packet requests deadline

• Training course deadline

• Quickpass deadline

• Special A/V requests

• Student/mentor forms due

6 April	“Call” day (phone/e-mail reminders to session chairs about 7 April)

7 April	• Detailed schedule of sessions due from session chairs to Wes & Charlotte (we expect to actually receive the schedules by 11-12 April)

22 April	Detailed schedule of sessions due to HQ from Wes & Charlotte (allows 15 calendar days for reviews, scheduling, working with session chairs, late reviews, etc.)

# 28 April	• Hotel cutoff

• Last-minute changes to text/info for final program. Note: this date should not be moved. The layout will need to be finalized and then it should have a minimum of 2 proofreadings; as-is, this is already a tight time frame to get it to the printer by 12 May.

12 May	Final program to printer (allows the printer 10 days for prep, print, and delivery by 27 May; this is minimum amount of time needed)

28 May	Conference begins