CBBIA SMALL GRANTS PROGRAM

APPLICATION FORM

Application No._____  (CBBIA use)

The conditions relating to Small Grants are detailed in ‘CBBIA Information about Small Grants’, which should be read before the application is completed.  The completed form plus should be emailed to CBBIA Project Administrator, Mr. Napoleon Tiapo, IAIA: Project@iaia.org. Alternatively the form can be completed in hard copy, either typewritten, or handwritten in dark ink, and set out clearly in the spaces provided.  The application may not exceed the three sides of the form. Please also supply signed supporting statements from two suitably qualified referees.

1. Title of proposal # THE NDZAH PLATEAU DAIRY FARMING GROUPS PROJECT, BANJA BAMENDA,CAMEROON

2. Name and address of applicant, and address: Fobizshi Eward Ndikum. The Program Co-ordinator, Cameroon Forest Shade Expansion (CAMFOSHEX) P.O BOX 155 BAMENDA , CAMEROON. Telephone number: (237) 756 97 01 Fax number: Email address: cfse2004@yahoo.com

3. Brief summary of the proposal Please explain its purpose and relevance to the CBBIA- objectives, the approaches and methods to be used, expected outputs and results 3a Background PROBLEM IDENTIFICATION During our field visit to access on the spot realities on the field, we came across the following problems to have been the main hindrance to this project: - Lack of improved modern cattle rearing skills - Inadequate group dynamism and management skills. - Lack of marketing strategies. ## ACTIVITIES - Measuring and partitioning the area into paddocks - Fencing the both external and internal partitions using dead and life fencing materials. - Land preparation and planting of grasses (gwatamala, brakeria and Kuitu grasses) - Construction of a complete Dip of reinforce concrete and wood. - Training courses for group members shall be held after every three months and a technician seminar shall be organized once a month for a year. ## STRATEGY - The group intends to provide all local materials needed to realise this project such as wood, land preparation and excavation. - CAMFOSHEX and the members will have to plan and come out with a work plan calendar which will enable them complete the said task within the maximum period of the programme plan. # IMPACT OF THE PROJECT To the environment To the population ENVIRONMENTAL IMPACT The continous flow of water in this area for cattle to drink and use in their Dip will keep the area wet, thus the vegetation in this region will remain ever green and fresh. Furthermore, farmers in this area will improve their yield with manure from the cattle dunk. The water catchment area from where this water supply is hanness will be protected by planting trees which will go a long way to reduce the amount of carbon dioxide in the atmosphere. External funding will be sorted from CBBIA-IAIA up to about 70% of the project cost. The veterinary services in Mezam shall assist in the provision of technical expertise to help in providing expert assistance to this program within the period which their technician is under training. 60 3b Objectives OBJECTIVES - To calve out the grazing area in to paddocks and improve on the fodder in the whole area. - To construct a cattle dip. - To organise workshops and training courses to train group members on: - Group dynamics - Management and catering - Marketing - Team work

Summary of proposal, cont. (use this page if necessary) # 3c Approaches and methods THE NDZAH PLATEAU FARMERS FARMING GROUPS Introduction In the context of efforts already deployed by several communities and individuals working for the improvement of cattle rearing in their bits to developing themselves and improving on the economic situation of the community. A group called the NDZAH PLATEAU FARMERS FARMING GROUP was formed, thanks to the dynamic efforts of CAMFOSHEX and 15 others FARMERS COMMOM INITIATIVE GROUPS in Bamenda. # THE GROUP AND THEIR PROJECT The NDZAH PLATEAU FARMERS FARMING GROUP was formed in 1996 with a total number of thirty four (34) cows, (7 bulls and 27 female cows). Within 1996 till date, the number of cattle have risen from 34 to 50 with (15 bulls and 35 female cows) giving a magnificient increase of 15 cattle as balance, given that the group was living and running from sales of at least three cows every year. During this period, the group was not carrying out organised cattle rearing coherently as the cattle were left to graze all over the village, feeding on very little or no rich fodder. This poor practice was due to lack of adequate knowledge in cattle rearing. Presently, the grazers have organised themselves more than before and acquire a large piece of land measuring up to 40 hectares in which they intend to paddock it out and improve the pasture within the whole area. They also intend to construct a dip and fish ponds. This idea, when they contacted ORICAA for a project formulation, was very much welcomed and encouraged. # PRESENTS ASSETS OF THE PROJECT The project has the following assets: - 40 hectares of land - 28 boundary pillars - 3 Farm houses - 3 Water points - Grass such as gwatamala, elephant stock etc - Materials like stone and gravel - 10km bulldozed road - Barb-wire fence, valued at 2.000.000 frs - Existing flock is 50 cattle valued 10.000.000 frs - Crops such as plantains, raffia palms etc. valued 1.500.000 frs - Eucalyptus and other trees valued 3.000.000 frs. 3d Expected outputs and results (clear deliverables should be identified) ## EXPECTED RESULTS The whole area of 40 hectares would have been calved out, partitioned into paddocks, fenced with dead and life fencing and planted with various grasses for cattle to feed on. A cattle dip would have been constructed using solid materials ready for use. 12 training courses would have been organised and trained group members in: - Group dynamics - Management and catering - Marketing

4. Details of costings and funding requirements ### ESTIMATE FOR A CATTLE DI NO DESCRIPTION UNIT QTY U.PRICE TOTAL 1 Site clearance M2 900 200 180.000 2 FOUNDATION 2.1 Excavation M3 14 1.000 14.000 2.2. Foundation concrete M3 12 9.000 108.000 2.3 Labour for concreting M3 10 20.000 200.000 Sub Total 5.020.000 3 CONCRETE FOR WALL OF DIP 3.1 Footpath M3 0.4068 150.000 150.000 3.2 Dip M3 9 10.000 90.000 3.3 External wall M3 12.48ms 12.000 149.7600 Sub Total 173.7600 4 POLES & SCANTLING FOR FOOT PATH 4.1 Scantling 4 x 8 x 500 Pcs 20 1.000 20.000 4.2 Eucalyptus poles Pcs 30 1.000 30.000 4.3 Nails Pkts 5 3.000 15.000 4.4 Rails Pcs 4 20.000 80.000 Labour Mdys 145.000 Sub Total 5 POLES & SCANTLING FOR OUTLET 5.1 Scantlings 4 x 8 x 500 Pcs 16 1.000 16.000 5.2 Eucalyptus poles Pcs 10 1.000 10.000 5.3 Nails Pkts 2 2.500 5.000 5.4 Labour Mdys 4 20.000 80.000 - CONCRETE FOR TANK AND - CHANNEL M3 0.20 9.000 40.000 Sub Total 151.000 7 FISH POND 7.1 Excavation M3 2.626 1.000 262.600 7.2 Construction of mount M3 0.375 75.000 225.000 7.3 Form work boards Pcs 4 3.500 14.000 7.4 Form work scantlings Pcs 7 2.000 14.000 7.5 Nails Pkt 5 2.500 12.500 - Labour for concreting and - form work mdys 4 20.000 80.000 Sub Total 595.600 Total for two fish ponds 829.000 GRAND TOTAL 8.487.200 frs CFA #### COST ESTIMATE FOR PASTURE IMPROVEMENT AND PADDOCK ##### NO DESCRIPTION UNITS QTY U. PRICE TOTAL 1 Site installation site 1 80.000 80.000 - Measuring and pegging round the complete area to be protected (perimeter) ml 15.000 25 375.000 - Digging of holes to implant a dead fence round the whole area of 40ha. And dropping poles into holes ml 15.000 50 750.000 4 Purchase of poles meant for fencing pcs 15.000 50 750.000 5 Purchase of barb-wire for dead fencing rolls 100 10.000 1.000.000 6 Assorted nails for fixing kg 150 700 105.000 7 Life fencing with trees such as Erithrina, cuttings and seeding including purchasing and planting ml 7.000 100 700.000 - Paddock with life/dead fencing within the whole area of 40.000 squ.m pd 100 10.000 1.000.000 - Land preparation in an area of 40.000m2 and grass planting like gwatamala etc M2 10.000 50 500.000 10 Purchase/transportation of grass to the farm M2 10.000 75 750.000 11 Maintenance and caring on farm to let grass grow well Maints 12 months 40.000 480.000 ###### Grand Total 6.490.000frs CFA. GENERAL TOTAL 14.977.200 frs CFA The whole area of 40 hectares would have been calved out, partitioned into paddocks, fenced with dead and life fencing and planted with various grasses for cattle to feed on. A cattle dip would have been constructed using solid materials ready for use. 12 training courses would have been organised and trained group members in: - Group dynamics - Management and catering - Marketing Amount sought from the CBBIA project  5.000.000 frs CFA

5. Names and addresses of two referees: At least one referee should be from a different place of work to the applicant. Referees must send their statements to IAIA before the closing date. Applicants should give the referees details of the proposal. 1. PENYEBHA SAMA CATHERINE, P.O BoX 54 Bamenda Cameroon. 2. Akum Prudentia Chah, P.O. Box 691 Bamenda Cameroon

6. Details of other applications (with addresses where appropriate), together with sums sought or awarded, for this proposal. Have not requested for award of grant anywhere.

7. Brief curriculum vitae (qualifications, employment) for main proposer: FOBIZSHI EDWARD NDIKUM Qualification: LLM Evironmental Law Employment: Nyoh Law Firm Jurist, Environmental Lawyer P O BOX 843 Bamenda cameroon

10.Declaration:I certify that the proposal to which this application refers is not supported through any initiatives other than those listed in ‘6’ (above). I confirm that the results of the work undertaken will be the property of the CBBIA. I also confirm my understanding that acceptance of a grant will imply a requirement for the proposed work to comply with the financial, monitoring and evaluation requirements of the CBBIA Program. Signature: Date: 12th August 2004

FOR CBBIA USE

| Received/Acknowledged | SC: Date / Decision | Amount awarded | Report/due |
| --- | --- | --- | --- |