# ANNEX                                    CONCEPTUAL FRAMEWORK

| Nº | Out put | Activities | Success Indicators |
| --- | --- | --- | --- |
| 01 | Identification of Medicinal Plants Conservation Areas Priotized medicinal plants list for focussed conservation action. | - Prepare inventory of medicinal plants and identify species of conservation concern - Organise workshops of field staff Threat Assessment of medicinal plants in the North West Province - Shortlist forest areas, which are rich in plant diversity and are traditionally reputed as sites for collection of medicinal plants. - Undertake field visits to the short-listed. Sites to make final selection of the sites suitable for establishment of medicinal plants conservation areas, based on: - Absence of biotic and abiotic pressures on the sites. - Presence of natural micro watershed and natural boundaries at the site - Local community support and NGO presence for establishment of medicinal plants conservation areas. - Accessibility of the sites to forest managers. - Presence of population of some of the species. | Final selection of medicinal plants conservation areas. Short-listing of threatened medicinal plants of with specific red-list status assigned to each. |
| 02 03 | Establishment and notification of medicinal plants conservation areas by the respective. Conduct detailed botanical documentation of medicinal plants conservation areas including collection of basic ecological data on each site. | 2.1 Demarcate physical boundaries of the selected sites. 2.2 Form local community management and protection committees wherever feasible. 3.1 Develop botanical and ecological survey documentation formats. 3.2 Develop sampling design for survey. 3.3 Contract field botanists to conduct surveys with the aid of local barefoot botanists drawn from community. 3.4 Computerize the data gathered from field surveys 3.5 Prepare herbarium records of species documented in every medicinal plant conservation areas. | Medicinal plants conservation areas identified and established on ground. Extent of medicinal plant diversity captured in the medicinal plants conservation areas network including presence of populations of red-listed species. |
| 04 | Develop action plans for a species recovery and enrichment programme for medicinal plants conservation areas for critically endangered and economically valuable species. Development of medicinal plants conservation action programme for medicinal plants conservation areas with clear focus on prioritised species | 41. Enlistment of the threatened and clinically important species for each medicinal plants conservation areas. 4.2 Estimation of population status of prioritised species in the medicinal plants conservation areas network. 4.3 Computerised data on natural distribution of the prioritised plants. 4.4 Organise collection of planting material (seeds) of prioritised species. 4.5 Computerised data on nursery techniques and seed storage methods of prioritised medicinal plants. 4. 6Train and involve communities to assist in collection of planting material and monitoring conservation status and other prioritised species. | Preparation of an operational plan for conservation action across the MPCA network in each state, focussed on prioritised species. |