CBBIA SMALL GRANTS PROGRAM.

# APPLICATION FORM

- TITLES OF PROPOSAL:

ENVIROMENTAL EDUCATION FOR SCHOOLS IN THE LIMBE

COMMUNITY.

- NAME AND ADDRESS OF APPLICANT:

MR. TANDUNGANG ALEXANDER PROGRAMME MANAGER

FOSHRUD CAMEROON.

B.P.575, LIMBE.

### TEL:(237) 7362499

FAX:237)3332475.

#### EMAIL:FOSHRUD @yahoo.com

- BRIEF SUMMARY OF THE PROPOSAL

(3a) Background: The pursuit for environmental conservation has been a significant    theme in development in the 21st century.  Conservationist says there is an inverse relation ship between human action    And the environment.  Problems such as soil erosion, loss of forest and wild life destruction, degradation of range and cultivable land etc, have been evident recently.  These problems require action to prevent further deterioration. Hence, the aspect of environmental education in the forefront. Its relevance will reflect to the development of comprehensive strategic action plan Which would protect the environment and manage the currently abundant natural   Resources of the country in a sustainable manner for the use and betterment of Present and future generation. Never the less, the first phase of this project started    Last year and the second phase commence October 2004, for which Foshrud is   Soliciting assistance. As a remark the target school was GBHS Limbe etc.

(3b) Objectives:

Global objectives: To ensure that environmental education is recognize and

An appropriately utilized tool protecting human health and the environment.

Finally help improve student academic achievement.

Specific Objectives:

- To ensure improved management and sustainable development of natural Resources by a greater understanding of the bio-diversity.

- Significantly to increase awareness, education, training and capacity building Amongst students by on-site field training.

- To determine the role of the environment on the academic and social life of Students and the community.

- To develop a model for the use of information on environmental conservation   and practice of sustainable development.

(3c) Approaches and Methods:

  - Intergrated teaching approach: Recognises the knowledge of mathematics,

Economics,geography and biology,as intergrated,thus forming the bases   of environmental education.

  - Fieldwork and demonstrations: The project shall use audio visual and flat teaching aids that will make Learning easy and encourage active learner-teacher interaction. Field trips to reserves and park site for suitable handled topics.

  - The Inquiry Approach:  This requires a conflict generated by an interest or a problem that commands the Attention of the students Problem–Solving Approach.

(3d) Expected outputs and Results:

(i) Expected Output:

- Environmental education included in the school curriculum.

- Students and the targeted community takes it as a culture in planting trees in their various environments in order to enhance   Afforestation.

- Environmental clubs created in schools to have acquaintance and be able to promote environmental management in communities by students and stake holders.

- Tree nurseries created by students and stakeholders to facilitate tree-planting exercises in the community.

- Results: Environmental education increases awareness and knowledge about

Environmental issues or problems. In doing so, it provides the public with the necessary skills to make informed Decision and takes responsible actions.

EE does not advocate a particular view points or cause of action rather

It teaches individuals how to weigh critical thinking and enhances

Their own problem –solving and decision making skills to improve our every day life  by protecting human health, advancing quality education, creating

Jobs, prompting environmental protection and encouraging stewardship of

Natural resources.

4- DETAILS OF COSTING AND FUNDING REQUIREMENT:

Programme Development: (OVER-ALL BUDGET)

1.	Personnel 1 Resource person  (fulltime) = 200.000FCFA MONTHLY=1800.000FCFA,for

## nine months.

Project coordinator (fulltime)=150.000FCFA    MONTHLY=1.350.000FCFA.

Administrative Assistant (fulltime)=100.000FCFA.   MONTHLY= 900.000FCFA.

Programme manager (fulltime)=250.000FCFA. MONTHLY=2.250.000fcfa.

TOTAL: 6.300.000FCFA

2.	Documentations/ Stationeries = 495.000FCFA.

3.	 Photography/Printing  = 63.500FCFA+95000FCFA    = 158.500FCFA

4.	 Transportation =3.600.000FCFA.

TOTAL=10.553.500FCFA.

In words, Ten million, Five Hundred and f Fifty Three Thousands, Five Hundred Francs

FCFA.

5.  Contingences  (10%) = 1.055.350FCFA.  Grand Total= 11.608.850FCFA

6.  Community Contribution (13%)= 1.509.150FCFA.

7.  Amount Sought from the CBBIA Project   =11.608.850-1.509.105FCFA.

=10.099.700FCFA.

# 5. NAMES AND ADDRESS OF REFEREES

(i) MR.BENJAMIN SERKFEM.

Programme Head, Environmental Education

and training- Limbe Botanic Garden, S.W.P.

Postal Code: 878  Limbe

Tel: 00237333 26 20/00237 776 19 96.

FAX: 00237 333 28 34.

### Email: bserkfem @ yahoo.co.uk

(ii) MR.FON IVO.

Network Development Officer.

SOPODEC-CAMEROON-HALFTIME.

POSTAL CODE: 1348 LIMBE.

TEL:00237 7711470.

Email: wanamah@yahoo.com

6. DATAILS OF OTHER APPLICATION

An application for collaboration proposal have

Been forwarded to the LIMBE BOTANIC GARDERN.

MINISTRY OF NATIONAL EDUCATION.

## 7. BRIEF CURRICULUM VITAE

MR.TANDUNGANG ALEXANDER.

PETROLEUM REFINING TECHNOLOGIST

WITH A DIPLOMA IN ANALYTICAL CHEMISTRY

ANDWORKING WITH SONARA-LIMBE, CAMEROON.

10. DECLARATION:

I certified that the proposal to which this application refers is not supported through any initiatives other than those listed in 6 (above). I confirm that the results of the work undertaken will be the property of the CBBIA. I also confirm my understanding that acceptance of a grant will imply a requirement for the proposed work to comply with the financial monitoring and evaluation requirements of the CIBBIA program

Signature: Tandungang Alexander					Date : 30th August, 2004

FOSHRUD- Cameroon.